Project Health & Status Report | PTB-STS-001  ·  Live status · 40% complete

One-page status the leaders actually read: red, amber or green against the approved schedule and budget baseline, with the variance in numbers — not adjectives. Progress is 40%; the programme is lagging ~10% on the critical path and ~12% over the planned phase budget.

| Document ID | PTB-STS-001 |
| --- | --- |
| Status / RAG | AMBER — LAGGING (schedule and cost red) |
| Progress | 40% overall vs 24-month roadmap (≈ month 9–10) |
| Schedule variance | ~10% behind plan on critical path / heavy activities (SV −10%, SPI ≈ 0.80) |
| Budget variance | ~12% actual vs planned phase budget (CV −12%, CPI ≈ 0.89) |
| Reported to | Project Sponsor (Sheikh Moeen Akhtar) and Executive Steering |

Section 1 — Project Overview & Executive Summary

Scope: 7 controlled deliverables (D1–D7) / 48 work packages. Schedule: 24-month critical path, ~40% elapsed, behind on heavy activities. Budget: approved USD 11.5M CAPEX / 27.5M TCO envelope; phase actual ~12% over plan. USD 0 released until DEC-02.

Executive summary (bad news first): schedule lag ~10% on the critical path and ~12% budget variance are the headline concerns. Immediate Sponsor decisions (DEC-01 effective date, DEC-02 funding release, DEC-03 delegation) are required to fund and authorise recovery.

Sections 3–4 — Progress & Schedule (Critical Path)

Variance in numbers: EV 40% vs PV ≈ 50% ⇒ SV −10%; SPI ≈ 0.80. M2 foundation (D2) ~2 months late; M3 copilot pilot (D3) slipping ~2–3 months behind plan (heavy activity).

| Milestone / deliverable | Baseline | Actual / status | Variance | Status |
| --- | --- | --- | --- | --- |
| M0 Schedule baseline approved | M1 | Approved | On track | OK |
| M1 Charter & funding gate | M02 | Approved; funding release open | 0 | OK |
| M2 Foundation accepted (D2) | M04 | Partially complete; data/vendor open | ~2 mo late | RED |
| M3 Copilot pilot live (D3) | M07 | Slipping (heavy activity) | ~2–3 mo late | RED |
| M4 Customer assistant (D4) | M11 | At risk with D3 | Attributable | AMBER |

Section 5 — Cost & Variance

Relation of variance: the ~12% cost variance tracks the ~10% schedule delay — heavy/critical-path work is costing more than planned. Reported in numbers (CV −12%, CPI ≈ 0.89), governed by the approved envelope, routed to the Sponsor (DEC-02/DEC-03), never absorbed silently.

| Measure | Value | Variance (numbers) | Status |
| --- | --- | --- | --- |
| Planned Budget (phase) | 100% plan | — | OK |
| Actual Cost (AC) | actuals from Finance | ~12% over plan | RED |
| Cost Variance (CV) | EV − AC | ~12% negative | RED |
| Cost Performance Index (CPI) | ≈ 0.89 | −11% | RED |
| Contingency use | being consumed | early-burn flag | AMBER |

Section 6 — Risks, Issues & Decisions Needed

What moved/fired on the register and what was done; then the 2–3 Sponsor-only calls, stated plainly with a recommendation.

| Risk / issue | Current | Action taken / recommendation |
| --- | --- | --- |
| Integration failure (D2) | FIRED — foundation slip | Front-load API/data profiling; DEC-10 catch-up |
| Vendor / platform slip | RISING — no vendor yet | Early sourcing; Sponsor decision DEC-07 |
| Staff / capacity | RISING — staffing open | DEC-05/DEC-06 appointments |
| Hallucination / model risk | MONITORING | Retrieval + handoff controls; pilot gates |
| Regulator concern | MONITORING | Compliance evidence pack; DEC-09 |

Decisions needed (Sponsor only): DEC-01 record effective date · DEC-02 release initial phase funding · DEC-03 delegate PM authority to act on the recovery. The report recommends, the Sponsor decides.