Project Charter | PTB-CHARTER-001  ·  Version 1.0  ·  Sponsor Approved 2 August 2026

| Document ID | PTB-CHARTER-001 |
| --- | --- |
| Version / date | Baseline 1.0 · submitted 31 July · approved 2 August 2026 |
| Status | Four-document pack approved · WBS correction incorporated 3 August 2026 |
| Project | Integrated AI Banking Implementation Ecosystem (Pair 5) |
| Organization | Pole Trust Bank, Toronto, Canada (synthetic classroom case) |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted; formal delegation via DEC-03) |

Element 1 — Purpose & Measurable Objectives

Purpose: replace fragmented AI experiments with a governed, phased enterprise capability improving customer service, employee productivity, lending operations and fraud investigation while preserving human accountability.

| Objective | Success target | Evidence owner |
| --- | --- | --- |
| Customer service | 35% fewer repetitive inquiries | Head of Contact Centre |
| Employee productivity | 30% less report-preparation time | COO |
| Lending quality | 35% less documentation rework | Head of Lending Operations |
| Fraud operations | 25% fewer false positives (pilot scope) | Head of Fraud Operations |
| Adoption & compliance | >60% adoption; zero critical breaches | Change Lead / CRO |
| Financial value | Positive NPV in 5-year horizon | CFO |

Element 2 — High-Level Scope

In scope

Enterprise AI governance + approved platform architecture · internal copilot MVP · customer digital assistant (approved knowledge + human handoff) · lending document-completeness/risk-summary support · fraud alert prioritization + investigator assist · API integration, data controls, audit logging, model monitoring, training, benefits measurement.

Out of scope

Autonomous loan/credit decisions · unsupervised financial advice/regulated communications · automatic account blocking/freezing · core-banking replacement · rollout beyond a use case that has not passed its evidence/compliance gate · execution/procurement commitments before delegated authority + funding.

Element 3 — Major Milestones & Budget Envelope

| Timing | Milestone | Approval evidence |
| --- | --- | --- |
| M1–2 | Initiation & business-case approval | Signed charter + funding gate |
| M3–4 | Governance & architecture | Governance model, target architecture, roadmap accepted |
| M5–7 | Internal copilot MVP | Pilot + prompt library accepted |
| M8–11 | Digital assistant MVP | Controlled customer pilot accepted |
| M12–15 | Lending support MVP | Human-authorized pilot accepted |
| M16–18 | Fraud enhancement MVP | Investigator-assist pilot accepted |
| M19–24 | Scale & closure | Benefits review, ops transition, closure report |
| Budget component | Envelope | Authorization treatment |
| Implementation CAPEX | $11.5M | Planning ceiling; not a funding release |
| Annual OPEX | $3.2M | Staged/annual funding decisions |
| Five-year TCO | $27.5M | Lifecycle envelope ($11.5M + $16.0M) |
| Initial release | $0 authorized | DEC-02 after CFO validation |

Element 4 — Top Risks & Foundational Assumptions

| Top risk | Required response | Owner |
| --- | --- | --- |
| Program complexity / benefit dilution | Phased delivery, scope control, stage gates | Sponsor / PM |
| Integration & data quality | API-first MVPs, profiling, lineage, fallback | CIO |
| Privacy, security, regulatory exposure | PIAs, access control, masking, logging | CRO / Privacy / CISO |
| Incorrect, biased, over-relied AI output | Approved sources, fairness/explainability, human authority | Model Risk lead |
| Low adoption / benefit overstatement | Training, champions, baselines, Finance attribution | Change Lead / CFO |

Assumptions to validate: sponsorship + phased funding remain · systems expose APIs · compliance supports controlled pilots · business owners supply capacity/data/baselines · Finance validates source estimates + cash-flow phasing.

Element 5 — Authority & Accountability

| Authority field | Position |
| --- | --- |
| Project Sponsor | Sheikh Moeen Akhtar — owns sponsorship + approval outcome |
| Project/Program Manager | Salman Zaman — working role; interim boundary active (DEC-03) |
| Stage-gate authority | DEC-04 proposes committee, quorum, reserved decisions |
| Escalation | Material risk/scope/KPI/roadmap/release → Sponsor |
| Financial authority | $0 authorized; DEC-02 release after CFO validation |

Element 6 — Approval & Sign-Off

| Capacity | Designation | Treatment |
| --- | --- | --- |
| Project sponsorship | Sheikh Moeen Akhtar | Approved · 2 Aug 2026 |
| Finance / Risk / Architecture | CFO / CRO / CIO | Concurrence deemed via Sponsor; release/readiness remain DEC-02/DEC-10/DEC-11 |
| Delivery acceptance | Salman Zaman | Working role accepted · DEC-03 delegation required |

Consolidated approval: Sponsor email dated 2 Aug 2026 confirms the four-document pack; funding, delegation and execution remain controlled prerequisites — the email does not authorize the full $27.5M TCO as immediate spend.