Scope Management Plan & Detailed Scope Statement | PTB-SCOPE-001  ·  Version 1.0

| Document ID | PTB-SCOPE-001 |
| --- | --- |
| Version / date | 1.0 / 2 August 2026 |
| Status | Refined planning baseline · Sponsor review |
| Project | Integrated AI Banking Implementation Ecosystem (Pair 5) |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted) |
| Change authority | Project Sponsor (or expressly delegated Steering under DEC-04) |
| Financial boundary | $11.5M CAPEX / $27.5M TCO; commitment authority $0 until DEC-02 |

Section 1 — Scope Management Approach

Product scope: governed enterprise AI ecosystem — one platform/control foundation + four human-accountable MVPs (copilot, customer assistant, lending support, fraud assist). Project scope: planning, architecture, readiness, MVP delivery, controlled pilots, training, adoption, benefits measurement, scale, transition, closure across 24 months.

Waterfall–Agile boundary: Waterfall governs scope baseline, funding, risk acceptance, exit gates. Agile squads refine stories inside an authorized phase without changing objectives, exclusions, KPIs, budget or roadmap. Backlog ≠ scope authority.

Section 2 — Scope Statement: Drawing the Line

| In scope | Out of scope |
| --- | --- |
| AI governance, acceptable-use, model oversight, gate evidence | Autonomous loan/credit/pricing decisions |
| Approved platform architecture + API layer | Unsupervised financial advice / regulated communications |
| Data classification, masking, access, retention, lineage, quality | Automatic account blocking/freezing |
| Internal copilot (approved knowledge, human verification) | Core-banking/CRM/loan/fraud-system replacement |
| Customer assistant (approved journeys, human handoff) | Ungated production scale |
| Lending completeness/risk summaries (human decisions) | Unapproved personal-data reuse / opaque operation |
| Fraud alert prioritization + investigator assist | New use cases/regions without change approval |
| Logging, audit, monitoring, fallback, support | Immediate commitment of full five-year TCO |
| Training, comms, champions, adoption | Vendor selection before assurance + Sponsor approval |
| Benefits baselines, scale, transition, closure | — |

Section 3 — Controlled Deliverables & Milestone Alignment

| ID | Deliverable | Window | Minimum completion evidence |
| --- | --- | --- | --- |
| D1 | Initiation & planning baselines | M01–02 | Approved charter; stakeholder/scope/schedule/cost/risk baselines |
| D2 | AI governance & architecture foundation | M03–04 | Governance model, target architecture, data/control design |
| D3 | Internal copilot MVP | M05–07 | Controlled pilot, knowledge/prompt library, access, measures |
| D4 | Customer digital assistant MVP | M08–11 | Journeys, handoff, privacy, audit trail, pilot |
| D5 | Lending decision-support MVP | M12–15 | Completeness/risk summaries, explainability, override, human authority |
| D6 | Fraud investigator-assist MVP | M16–18 | Prioritization, thresholds, investigator review, no auto-action |
| D7 | Scale, transition & closure | M19–24 | Scale decision, support model, benefit review, closure report |

Section 4 — Work Breakdown Structure (8 / 16 / 48)

| L1 branch | L2 deliverables (2 per branch) | WP |
| --- | --- | --- |
| 1.0 Governance | 1.1 Authorization/baselines · 1.2 Delivery/assurance/benefits | 6 |
| 2.0 AI Foundation | 2.1 Responsible AI/architecture/platform · 2.2 Data/security/model-ops | 6 |
| 3.0 Internal Copilot | 3.1 Use cases/requirements/knowledge · 3.2 Config/assurance/pilot | 6 |
| 4.0 Customer Assistant | 4.1 Journeys/knowledge/privacy · 4.2 Orchestration/assurance/pilot | 6 |
| 5.0 Lending Support | 5.1 Requirements/intake/evidence · 5.2 Controls/assurance/pilot | 6 |
| 6.0 Fraud Assist | 6.1 Signals/data/triage · 6.2 Controls/assurance/pilot | 6 |
| 7.0 Change & Benefits | 7.1 Readiness/comms/learning · 7.2 Adoption/KPIs/benefits | 6 |
| 8.0 Scale & Closure | 8.1 Scale/release/stabilization · 8.2 Transition/handover/closure | 6 |
| Total | 16 L2 deliverables | 48 L3 |

Section 5 — Acceptance Criteria & Objective Traceability

| Approved objective | Deliverable | Acceptance evidence | Owner |
| --- | --- | --- | --- |
| 35% fewer customer inquiries | D4 / M08–11 | Baseline + pilot; knowledge/handoff/audit evidence | Contact Centre / Digital PO |
| 30% less report-prep time | D3 / M05–07 | Time study + governed use cases + verification | COO / Copilot PO |
| 35% less lending rework | D5 / M12–15 | Rework baseline + traceable summaries + override | Lending Ops / Credit Risk |
| 25% fewer fraud false positives | D6 / M16–18 | Labelled sample + monitoring + no auto-action | Fraud Ops / Fin-Crime |
| >60% adoption | D3–D7 | Active-use rule + dashboard + readiness | Change Lead / PO |
| Zero critical breaches | D2–D7 | Severity definition + checklist + incident records | CRO / Compliance |
| Positive NPV (5-yr) | D1/D7 | Finance-approved timing + attribution | CFO |

Section 6 — Assumptions, Constraints, Dependencies

| Assumptions | Constraints | Dependencies |
| --- | --- | --- |
| Sponsorship + phased funding remain | 24-month roadmap | Governance + architecture evidence |
| Systems expose APIs | $11.5M CAPEX / $27.5M TCO; $0 until DEC-02 | Vendor selection + due diligence |
| Compliance supports controlled pilots | Canadian regulatory applicability (DEC-09) | Data, privacy, security, model-risk review |
| Owners supply capacity/data/baselines | PM delegation + Steering via DEC-03/04 | System integration readiness |
| Finance validates source estimates | Human accountability + gates non-negotiable | Business/training/Finance capacity |

Section 7 — Validation, Change Control & PM Boundary

Validation: Product Owner assembles evidence → control functions review → PM confirms traceability → functional owner records validate/conditions/not-validated → Sponsor decides stop/remediate/continue/scale/close.

Change workflow: Log → Triage → Assess → Review → Decide (Sponsor) → Rebaseline → Verify.

PM working-role boundary (6 controls):

| Permitted | Reserved for Sponsor |
| --- | --- |
| Maintain baselines, registers, traceability | Commit/release funds |
| Convene workshops, coordinate functions | Engage/contract vendor |
| Prepare assessments, recommendations, gate packs | Direct staff outside assignments |
| Record decisions, evidence, escalations | Approve material scope/KPI/TCO changes |
| Coordinate acceptance evidence, report status | Accept regulatory/model/residual risk |
| Recommend stop/remediate/continue/scale | Authorize pilot/release/scale unless delegated |