Schedule Management Plan & Work-Package Sequencing | PTB-SCHED-001  ·  Version 1.0

| Document ID | PTB-SCHED-001 |
| --- | --- |
| Version / date | 1.0 / 2 August 2026 |
| Status | Refined planning baseline · Sponsor review |
| Project | Integrated AI Banking Implementation Ecosystem (Pair 5) |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted) |
| Schedule change authority | Sponsor; milestone slip outside tolerance routes to Sponsor until DEC-03/04 |
| Open decisions | Effective date (DEC-01) · owners (DEC-05) · readiness (DEC-10) |

Section 1 — Schedule Approach, Purpose & Methodology

Purpose: sequence the 48 work packages into a realistic, controllable 24-month schedule; expose the zero-slack chain so management attention lands where delay extends delivery; fix a baseline for progress, variance and corrective action.

Methodology: Precedence Diagramming Method (PDM) on 48 work packages, rolled up to 7 deliverables. Finish-to-start dominates; start-to-start/finish-to-finish only where parallelism is evidenced. Waterfall gates control phase exit; Agile sprints refine detail inside an authorized phase without changing the baseline.

Section 2 — Dependencies & Critical Path

Critical path = D1→D2→D3→D4→D5→D6→D7 (zero slack, 24 months).

| Deliverable | Window | Depends on | Zero-slack reason |
| --- | --- | --- | --- |
| D1 Initiation & baselines | M01–02 | Sponsor authorization (DEC-01) | Anchor start; effective date not yet approved |
| D2 Governance & architecture | M03–04 | D1 + DEC-10 readiness | Every MVP needs shared platform |
| D3 Internal copilot | M05–07 | D2 complete | First release after foundation gate |
| D4 Customer assistant | M08–11 | D3 pilot evidence | Reuse foundation + copilot controls |
| D5 Lending support | M12–15 | D4 complete | Needs service integration |
| D6 Fraud assist | M16–18 | D5 complete | Needs prior integration |
| D7 Scale & closure | M19–24 | D6 pilot evidence | Needs cross-pilot evidence |

Float note: change/adoption (7.0), benefits and model-ops are parallel (float) — not on the critical path but must still clear their own gates.

Section 3 — Board-Visible Milestones

| Milestone | Timing | What the board sees | Gate evidence | Owner |
| --- | --- | --- | --- | --- |
| M0 Baseline approved | M1 start | Effective date locked | DEC-01 authorization | Sponsor |
| M1 Charter/funding gate | End M02 | Initiation approved | Charter + funding gate | Sponsor |
| M2 Foundation accepted | End M04 | Platform ready | Governance/architecture (DEC-10) | CIO/EA |
| M3 Copilot pilot live | End M07 | First MVP live | Pilot + prompt library | Copilot PO |
| M4 Customer pilot live | End M11 | Customer pilot live | Controlled customer pilot | Digital PO |
| M5 Lending pilot live | End M15 | Lending pilot live | Human-authorized pilot | Lending PO |
| M6 Fraud pilot live | End M18 | Investigator pilot live | Investigator-assist pilot | Fraud PO |
| M7 Rollout done | End M24 | Scaled, transitioned | Benefits + ops transition + closure | Sponsor |

Section 4 — Work-Package Sequencing (WBS → Schedule)

| WBS | Branch | Window | Predecessor | Accountable |
| --- | --- | --- | --- | --- |
| 1.0 | Governance | M01–24 | Sponsor authorization | Sponsor / PM |
| 2.0 | AI Foundation | M03–04 | 1.0 baseline | CIO / EA |
| 3.0 | Internal Copilot | M05–07 | 2.0 foundation gate | COO / Copilot PO |
| 4.0 | Customer Assistant | M08–11 | 3.0 pilot evidence | Digital PO |
| 5.0 | Lending Support | M12–15 | 4.0 complete | Lending PO |
| 6.0 | Fraud Assist | M16–18 | 5.0 complete | Fraud PO |
| 7.0 | Change & Benefits | M01–24 (parallel) | 1.0 (parallel 2–6) | Change Lead / CFO |
| 8.0 | Scale & Closure | M19–24 | 6.0 pilot evidence | Sponsor / PM |

Section 5 — Schedule Risks & the Two Riskiest Dependencies

| Risk | Response | Owner |
| --- | --- | --- |
| Foundation slip delays all MVPs | Front-load architecture/data/control evidence | CIO / EA |
| Vendor lead time exceeds window | Early sourcing, parallel due diligence, go/no-go | Procurement / PM |
| Owner capacity unconfirmed | Nominate POs before requirements (DEC-05) | Sponsor / PM |
| Unrealistic sprint optimism | Agile output cannot advance gate without evidence | Sponsor / PM |
| Milestone slippage hidden | Weekly variance + escalate > tolerance | PM / AI PMO |

Riskiest dependency 1 — Enterprise-foundation acceptance: D2 gates every MVP; zero slack; any slip extends D3–D7 one-for-one.

Response: CIO validates readiness before build (DEC-10); fallback is a reduced pilot boundary, not a silent slip.

Riskiest dependency 2 — Vendor & platform selection: no vendor selected; sourcing lead time is external and incompressible.

Response: approved sourcing + due diligence early (DEC-07); no vendor named before security/privacy/legal/third-party-risk evidence.

Section 6 — Schedule Validation, Control & Baseline

| Validation | Control | Baseline definition |
| --- | --- | --- |
| Every WP has owner + predecessor | Weekly variance; escalate > tolerance | Effective start date (DEC-01) |
| Critical path = 24 months | Roadmap/milestone change → Sponsor | 7 board milestones locked |
| Milestones map to charter gates | Agile backlog ≠ baseline change | Critical path D1→D7 frozen |
| No date without evidence owner | DEC-01/03/04/10 close authority | Integrated with WBS/RACI/decisions |