Cost Estimate & Budget Planning | PTB-COST-001  ·  Version 1.0

| Document ID | PTB-COST-001 |
| --- | --- |
| Version / date | 1.0 / 2 August 2026 |
| Status | Refined planning baseline · Sponsor review |
| Project | Integrated AI Banking Implementation Ecosystem (Pair 5) |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted) |
| Cost change authority | Sponsor; movement outside envelope routes to Sponsor until DEC-02/03 |
| Funding authority | $0 authorized; DEC-02 release after CFO validation |

Section 1 — Cost Management Approach & Methodology

Plan Cost Management: estimate at work-package level, roll up to 7 deliverables / 8 WBS branches. Bottom-up as primary method, cross-checked top-down against the source package.

Determine Budget: aggregate estimates → add explicit contingency (state what it covers) → fix the cost baseline. Management reserve stays outside the baseline, Sponsor-controlled.

Grounding rule: the instructional slide's "CAD 1.9M envelope" is a generic template placeholder — this plan reconciles to Pole Trust's approved $11.5M CAPEX / $27.5M TCO; the placeholder is not imported as fact.

Section 2 — Cost Estimates (Per Work Package, Rolled Up)

| WBS | Branch | Bottom-up (USD) | Top-down check | Accuracy |
| --- | --- | --- | --- | --- |
| 1.0 | Governance | $1.15M | ~10% CAPEX | +25% / −10% |
| 2.0 | AI Foundation | $3.45M | ~30% CAPEX | +25% / −10% |
| 3.0 | Internal Copilot | $1.44M | ~12.5% CAPEX | +25% / −10% |
| 4.0 | Customer Assistant | $1.73M | ~15% CAPEX | +25% / −10% |
| 5.0 | Lending Support | $1.44M | ~12.5% CAPEX | +25% / −10% |
| 6.0 | Fraud Assist | $1.44M | ~12.5% CAPEX | +25% / −10% |
| 7.0 | Change & Benefits | $0.86M | ~7.5% CAPEX | +25% / −10% |
| 8.0 | Scale & Closure | $0.86M | ~7.5% CAPEX | +25% / −10% |
| Roll-up | 8 branches | $12.37M | vs $11.5M ceiling | +7.6% delta |

Section 3 — Budget, Contingency & Baseline

| Component | Amount | What it covers |
| --- | --- | --- |
| Work-package roll-up | $12.37M | Bottom-up sum of 8 branches |
| Approved CAPEX ceiling | $11.5M | Binding source-approved envelope |
| Contingency reserve | Finance-sized | Known-unknown estimate risk (DEC-02) |
| Management reserve | Sponsor-held | Unknown-unknowns + approved changes |
| Annual OPEX | $3.2M | Recurring post-implementation cost |
| Five-year OPEX | $16.0M | $3.2M × 5 |
| Five-year TCO | $27.5M | $11.5M + $16.0M (lifecycle, not spend) |

Reconciliation: roll-up $12.37M exceeds $11.5M ceiling by $0.87M (7.6%) → estimate is capped at the ceiling; the delta is logged as an open Finance item (DEC-02), not presented as an approved increase.

Section 4 — Cost Baseline & Reconciliation Math

| Line | Amount | Derivation |
| --- | --- | --- |
| Approved CAPEX | $11.5M | Source-approved charter envelope |
| Annual OPEX | $3.2M | Source-approved run-rate |
| Five-year OPEX | $16.0M | $3.2M × 5 |
| Five-year TCO | $27.5M | $11.5M + $16.0M |

The math: $11.5M + ($3.2M × 5) = $11.5M + $16.0M = $27.5M. This is the reconcile target — not an authorization to spend, which stays $0 until DEC-02.

Section 5 — Cost Control, Earned Value & Variance Thresholds

| EVM measure | Definition | Threshold |
| --- | --- | --- |
| PV | Planned Value (authorized budget for planned work) | Monthly baseline curve |
| EV | Earned Value (budget of work completed) | Progress vs scope/schedule |
| AC | Actual Cost (cost incurred) | Finance actuals |
| CV | EV − AC | Escalate if < −10% of EV |
| SV | EV − PV | Escalate if < −10% of PV |
| CPI | EV ÷ AC | Flag < 0.95 |
| SPI | EV ÷ PV | Flag < 0.95 |
| Variance | Tolerance outside baseline | Sponsor escalation beyond ±10% |

Control rule: monthly reporting reconciles EV/PV/AC against baseline; variance beyond threshold triggers corrective action + Sponsor escalation. No overrun is silently absorbed.

Section 6 — Cost Validation, Control & Baseline Acceptance

| Validation | Control | Baseline definition |
| --- | --- | --- |
| Every WP has bottom-up estimate + owner | Monthly reporting + variance thresholds | CAPEX ceiling $11.5M frozen |
| Roll-up reconciles to CAPEX ceiling | Funding $0 until DEC-02 | TCO $27.5M locked |
| Contingency explicit + risk-based | Baseline change → Sponsor | Contingency vs reserve separated |
| EVM defined against baseline | Contingency use logged, not hidden | EVM integrated with WBS/schedule |