Communications Management Plan | PTB-COMM-001  ·  Version 1.0  ·  Planning baseline · Sponsor review

Section 1 — Communications Approach, Purpose & Methodology

Purpose: build a shared, accurate and timely picture of the programme for every stakeholder group; reduce uncertainty, resistance and rumour; and give people the information they need to decide, act and support delivery (PMBoK Plan Communications Management).

Method: audience-by-audience analysis from the approved Stakeholder Register — what each audience needs, how often, through which channel, with a single accountable sender. No material claim is made without an approved source.

| Document ID | PTB-COMM-001 |
| --- | --- |
| Version / date | 1.0 / 2 August 2026 |
| Status | Refined planning baseline · Sponsor review |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted) |
| Comms change authority | Sponsor; external/regulatory or fact-changing messages route to Sponsor until DEC-03/04 |

Section 2 — Audiences, Needs & Channels

Each audience is defined by what it needs, how often, through which channel, and the accountable sender. The contact-centre message is the hardest and is drafted early.

| Audience | What they need | Frequency | Channel | Accountable sender |
| --- | --- | --- | --- | --- |
| Board & Executive Steering | Progress, risks, decisions, funding, gates | Monthly + every gate | Decision pack, dashboard, meeting | Sponsor / PM |
| Staff & target users | What the programme means for their work, timeline, training | Monthly + each pilot | Intranet, town hall, briefing | PM / Change Lead |
| Union & employee reps | Role impact, workload, monitoring fairness, how concerns are heard | Monthly + impact events | Rep forum, written brief | PM / HR / Change |
| Contact-centre agents | How the assistant changes Tier-1 work, what stays human, support | Before pilot + go-live | Manager cascade, huddle, FAQ | Contact Centre Lead / PM |
| Regulator & compliance | Obligations, evidence, incidents, assurance status | Per obligation | Regulatory liaison, evidence pack | Legal / Compliance |
| Customers | Service change, privacy, accessibility, human escalation | At customer pilot | Statement, in-app notice, CX review | Digital PO / CX |

Section 3 — Stakeholder Communications Matrix

Maps the approved stakeholder universe to a concrete communications action, cadence, channel and sender. Exactly one accountable sender per row — two accountables means none.

| Stakeholder / group | Key message | Cadence | Channel | Accountable sender |
| --- | --- | --- | --- | --- |
| Sponsor & Steering | Gate decisions, risks, funding, approval | Monthly + every gate | Decision pack, meeting | Project/Program Manager |
| CDO | Digital value, product coherence, pilot readiness | Fortnightly | Value/design review | Digital Product Owner |
| CIO & Architecture | Architecture, integration, readiness evidence | Weekly (foundation) | Architecture workshop | Architecture Lead |
| Risk, Compliance, Legal, Privacy | Control evidence, obligations, assurance | Weekly + per gate | Control checklist, escalation | Risk / Compliance Lead |
| CFO / Finance | Cost, benefits, funding, attribution | Monthly | Cost & benefit review | Finance Lead |
| Contact Centre leadership & agents | Assistant scope, handoff, training, support | Before pilot + go-live | Cascade, huddle, FAQ | Contact Centre Lead |
| HR, Learning & Change | Role impact, training, adoption support | Monthly | Change council | Change Lead |
| Vendor / procurement (future) | Sourcing, due diligence, contract obligations | Per sourcing stage | Procurement record | Procurement Lead |
| Customers & CX | Service change, privacy, accessibility, escalation | At customer pilot | Statement, in-app notice | Digital Product Owner |
| Regulators / obligations | Applicable obligations, evidence | Per obligation | Regulatory liaison | Legal / Compliance |

Section 4 — Key Messages & Announcements

Programme announcement: governed, human-accountable AI, phased and evidence-gated, never autonomous on money or accounts.

Contact-centre announcement (drafted first): "Your Tier-1 work is not being automated away. The assistant absorbs repetitive, low-complexity inquiries; you remain the accountable human for judgement, empathy and escalation. We will train you, measure the change transparently and keep your handoff authority intact."

| Announcement | Audience | Draft owner | Approval | Channel / timing |
| --- | --- | --- | --- | --- |
| Programme kick-off | All staff | PM | Sponsor | Intranet + town hall / M01 |
| Copilot pilot | Target users | Copilot PO | PM | Team briefing / M05 |
| Contact-centre assistant | Agents + union reps | Contact Centre Lead | Sponsor | Cascade + forum / before M08 |
| Customer-facing notice | Customers | Digital PO | Sponsor + CX | In-app + statement / at pilot |

Section 5 — Escalation & Incident Communications

Material risk, compliance, budget, scope, KPI, roadmap or release matters route to the Sponsor; external and regulatory incident communications require Sponsor approval.

| Area | Control |
| --- | --- |
| Escalation route | Weekly variance vs baseline; escalate outside tolerance · material risk/compliance event → Sponsor within 24h · no unilateral external statement · DEC-03/04 close delegated thresholds |
| Incident communications | Internal: affected teams briefed first · external/regulatory: Legal/Compliance drafts, Sponsor approves · every incident communication recorded · DEC-11 governs residual-risk acceptance |
| Rumour / misinformation | Single source of truth: this plan + decision register · correct inaccuracies promptly via the same channel · escalate persistent misinformation to Sponsor · keep staff/union messages consistent |

Section 6 — Validation, Control & Baseline

Definition of a valid communications baseline: audience-led (every group has a need, cadence, channel, sender) · single-accountable (exactly one A per message) · controlled (external/regulatory messages route to the Sponsor; open authority closes through PTB-DEC-001).