Resource Management Plan & Deliverable RACI | PTB-RES-001  ·  Version 1.0  ·  Planning baseline · Sponsor review

Section 1 — Resource Approach, Purpose & Methodology

Purpose: ensure every major deliverable has the people, roles, skills and capacity it needs, when it needs them, without over-committing the bank’s staff (PMBoK Plan Resource Management), explicitly tied to scope, schedule, cost, risk and the WBS.

Method: resource needs derive from the 48-work-package WBS and the D1–D7 deliverable windows. Roles are named where the bank has confirmed them; where people are not yet freed, the gap is stated explicitly rather than assumed away.

| Document ID | PTB-RES-001 |
| --- | --- |
| Version / date | 1.0 / 2 August 2026 |
| Status | Refined planning baseline · Sponsor review |
| Project Sponsor | Sheikh Moeen Akhtar |
| Project/Program Manager | Salman Zaman (working role accepted) |
| Resource change authority | Sponsor; staffing/procurement/resourcing commitments route to Sponsor until DEC-03/06 |

Section 2 — Resource Types & Loading

Resources are identified by type, matched to the WBS branch and schedule window, and loaded against the approved roadmap. Capacity the bank has not freed is flagged as a gap, not silently absorbed.

| Resource type | Examples | WBS branch | Schedule window | Capacity status |
| --- | --- | --- | --- | --- |
| Human | PM, product owners, squads, control leads, trainers | 1.0–8.0 | M01–M24 | Partial — gaps flagged in Section 4 |
| Material / tooling | AI platform, data tools, test environments | 2.0 | M03–M04 | Not procured — DEC-07 |
| Financial | Approved CAPEX envelope, staged funding | 1.0–8.0 | M01–M24 | $0 released until DEC-02 |
| Information | Approved knowledge, data, controls, evidence | 2.0–7.0 | M03–M24 | Data readiness open — DEC-10 |
| Physical | Workspaces, infrastructure, network capacity | 2.0–8.0 | M03–M24 | Confirmed as required by architecture |

Section 3 — Deliverable RACI

Every major deliverable (D1–D7) is assigned an R, A, C and I. Exactly one A per row — two accountables means none. Real roles are named where confirmed; otherwise the designation is stated and routed through DEC-05.

| Deliverable | R (does) | A (owns) | C (consults) | I (informed) |
| --- | --- | --- | --- | --- |
| D1 Initiation & baselines | Salman Zaman (PM working role) | Project Sponsor | Steering, Finance, Control leads | All stakeholders |
| D2 Governance & architecture | Architecture / Data leads | CIO & Enterprise Architecture | Security, Privacy, Risk, Model Risk | Steering, Sponsor |
| D3 Internal copilot MVP | Copilot squad | COO / Copilot Product Owner | Risk, Security, Change, HR | Steering, Sponsor |
| D4 Customer assistant MVP | Digital-assistant squad | Retail / Digital Product Owner | Contact Centre, CX, Privacy, Legal | Steering, Sponsor |
| D5 Lending support MVP | Lending squad | Lending Product Owner | Credit Risk, Compliance, Lending Ops | Steering, Sponsor |
| D6 Fraud investigator-assist MVP | Fraud squad | Fraud Product Owner | Financial Crime, Risk, Model Risk | Steering, Sponsor |
| D7 Scale, transition & closure | Operations / IT service leads | Project Sponsor | Finance, HR, Change, ITSM | All stakeholders |

Section 4 — Capacity Gaps & Responses

Where the plan needs people the bank has not yet freed, the gap is stated explicitly with a named response and owner. No gap is silently absorbed into an assumption.

| Resource gap | Impact | Response | Owner | Closure |
| --- | --- | --- | --- | --- |
| Product Owners not nominated | Requirements acceptance cannot start | Nominate through DEC-05 before affected gate | Sponsor / CDO | DEC-05 |
| AI PMO / squad capacity unconfirmed | Delivery coordination and build capacity | Confirm resources via functional assignment records | PM / functional leads | DEC-06 |
| Vendor / platform team not selected | Foundation configuration and MVP build | Run approved sourcing and due diligence early | Procurement Lead | DEC-07 |
| Data / MLOps capacity unconfirmed | Data foundation and model operations | Confirm Data Science / MLOps owners before build | CIO / Data Owner | DEC-10 |
| Change / training resources unconfirmed | Adoption and readiness | Assign Change Lead and trainers before first baseline | COO / Change Lead | DEC-05 |
| Compliance / control review capacity | Gate evidence and approval | Reserve control-review capacity per gate; escalate contention | Compliance Lead / PM | DEC-03/04 |

Section 5 — Resource Control & Baseline

Validation: every deliverable has an R, A, C and I with exactly one accountable · real roles named where confirmed · gaps stated, not assumed. Control: loading levelled against the critical path · staffing/procurement routes to Sponsor · gap closures logged with evidence · DEC-03/05/06/07 close open authority.

Definition of a valid resource baseline: deliverable-mapped (full RACI per deliverable) · honest about gaps (people the bank has not freed are flagged with a response) · controlled (staffing/procurement routes to the Sponsor through PTB-DEC-001).