Project Change Control | PTB-CHG-001  ·  Integrated change control · Live

The scope-creep firewall (PMBoK Perform Integrated Change Control). Every change is logged in writing, assessed for impact against the baseline, decided by the Change Control Board (CCB), and enters the change log. The baseline only moves through this door. Documents a live, fully-filled change request (CR-002) submitted for CCB/BOG review.

| Document ID | PTB-CHG-001 |
| --- | --- |
| Regime | Integrated Change Control (PMBoK); CCB decision authority |
| Scope anchor | PTB-SCOPE-001 wrote exclusions out by name (e.g. module 3) |
| Decision authority | Sponsor-led CCB (BOG); PM evaluates; Sponsor decides |
| Project Sponsor | Sheikh Moeen Akhtar |
| Related controls | DEC-02 (funding), DEC-03 (delegation), DEC-04 (Steering), PTB-STS-001 (status report) |

Sections 1–3 — Request, Identification, Reason & Impact

The executive wants module 3 added mid-flight — it goes on a change request form, in writing, and is uniquely identified (CR-###) with the reason stated. Impact (cost, schedule, risk, benefit) is assessed against the baseline; in AI drafts you verify before the CCB sees it.

| Dimension | Assessment vs baseline | Evidence |
| --- | --- | --- |
| Scope | Adds/removes vs PTB-SCOPE-001 | Scope statement, WBS |
| Schedule | Critical path (D1–D7), milestones, 24-month roadmap | PTB-SCHED-001 |
| Cost | Budget, contingency, CAPEX/OPEX envelope | PTB-COST-001, variance |
| Risk | New/changed risks, triggers, owners | PTB-RISK-001 |
| Benefit | Value/cost, KPI and NPV effect | Benefits baseline |

Sections 4–5 — Approval & Decision, Change Log

The CCB approves, rejects or defers — not the loudest voice in a hallway. Approved or not, every change enters the change log; the baseline only moves through this door.

| Decision | Meaning | Next step |
| --- | --- | --- |
| Approved | Enters the baseline | Log, rebaseline, update schedule/cost/scope/risk |
| Rejected | Baseline preserved | Log the rejection with reason |
| Deferred | Revisit at a later gate | Log with next review date |

Change Request CR-002 — Submitted for CCB/BOG Decision

Live, fully-completed change request raised from execution (not a template). All six change-log ingredients filled in and submitted for decision, linked to the Status Report variance finding.

| # | Change-log element | Filled entry for CR-002 |
| --- | --- | --- |
| 1 | Change identification | CR-002 · Requester: Salman Zaman (PM) · Source: PTB-STS-001 · Baselines: PTB-SCHED-001 (D2/D3), PTB-COST-001 · WBS 2.0/3.0 |
| 2 | Reason of change | ~10% behind plan on the critical path (D2 foundation, D3 copilot) and ~12% over phase budget; authorise DEC-02 funding release and controlled rebaseline |
| 3 | Impact of change | Schedule: funds D2/D3 catch-up (recovery). Cost: releases DEC-02 phase funding vs USD 11.5M/27.5M envelope. Risk: reduces integration/vendor-slip. Benefit: protects KPI/NPV timeline |
| 4 | Justification | Evidenced by PTB-STS-001 (SV -10%, SPI ~0.80; CV -12%, CPI ~0.89); funding/rebaseline only — no scope added |
| 5 | Approval | FOR CCB/BOG DECISION · Sponsor (Sheikh Moeen Akhtar) decides · advised by PM/Finance/CIO/Risk |
| 6 | Log | Logged as CR-002 · status FOR CCB DECISION · linked to DEC-02 |

Execution note: CR-002 is the change request the Status Report "Decisions needed" (DEC-01/DEC-02/DEC-03) routes through. It enters the log before any decision — approved or not — and the baseline moves only through this door.

Section 6 — Validation, Control & Baseline

Definition of a valid change-control baseline: every change is on a form in writing with a unique ID · reason and impact verified · justification evidenced · CCB decision recorded · everything logged · the baseline moves only through an approved logged change. The change log is the traceable source of truth.