## Slide 1
POLE TRUST BANK (PTB)-CHANGE REQUEST (CR)-001 | CHANGE REQUEST (CR)-002 | STATUS: FOR CHANGE CONTROL BOARD (CCB) DECISION
Project Change Control
Pole Trust Bank (PTB) | AI Banking Transformation
Decision Authority: Project Sponsor — Sheikh Moeen Akhtar

## Slide 2
The Change Control Firewall — How Pole Trust Bank (PTB) Protects Its Baseline
Without Change Control
Unapproved scope creep. Cost overruns. Timeline slippage. No audit trail. No accountability.
The Firewall
Written submission. Unique ID. Impact assessed. Change Control Board (CCB) decides. Decision logged. Baseline updated only after approval.
The Result
Traceable baseline. Documented decisions. Protected delivery. Governance accountability.
Change Raised
Impact Assessed
Change Control Board (CCB) Decides
Logged

## Slide 3
No Change Reaches the Change Control Board (CCB) Without Full Impact Assessment
Every Change Control Board (CCB) change request must include a verified five-dimension impact assessment under Pole Trust Bank Change Control (PTB-CHG-001). It gives the Change Control Board (CCB) the factual basis needed for a defensible decision. Each dimension maps to a baseline document and evidence source.
Scope
What is added or removed from PTB-SCOPE-001.
Schedule
Impact on the critical path, milestones, and roadmap.
Cost
Impact on budget, contingency, and Capital Expenditure/Operating Expenditure (CAPEX/OPEX).
Risk
New risks, changed triggers, and updated ownership.
Benefit
Effect on value-to-cost ratio, Key Performance Indicators (KPIs), and Net Present Value (NPV).

## Slide 4
Change Request CR-002 — Live Change Request | FOR Change Control Board (CCB) DECISION
FUNDING + REBASELINE ONLY — NO SCOPE ADDED
Change Request CR-002 is a live change request under Pole Trust Bank Change Management Procedure (PTB-CHG-001). It seeks DEC-02 funding release and a controlled schedule rebaseline based on Pole Trust Bank Status Report (PTB-STS-001) Earned Value Management (EVM) variances. No new scope, deliverable changes, or Work Breakdown Structure (WBS) changes are included. The six cards below are the full Change Request CR-002 record for Change Control Board (CCB) review.
1
Change ID
CR-002
2
Reason
Schedule Delay: Late D2 start (data gaps, vendor onboarding). D3 single-threaded, zero-slack critical path. M2/M3 delayed 2-3 months; M4 at risk. | Cost Overrun: D2/D3 specialist effort + extended procurement. Within USD 11.5M CAPEX / USD 27.5M TCO envelope but unsustainable trajectory.
3
Impact Summary
Schedule: M0/M1 closed. M2/M3 red (2-3 month delay). M4 amber/at risk. | Cost: Specialist labor + procurement overrun. Within envelope but trajectory unsustainable. | Risk: Compressed recovery increases D2/D3 execution risk. Vendor dependencies critical. | Benefit: Delayed value realization. KPI/NPV protection requires accelerated D2/D3 recovery.
4
Decision Authority
FOR Change Control Board (CCB)/Board of Governors (BOG) DECISION.

## Slide 5
Change Request CR-002 Is Evidenced — Not Assumed
Schedule Performance Index (SPI)
0.80
Below Target
Cost Performance Index (CPI)
0.89
Below Target
CR-002 DOES
✓ Release DEC-02 Funding
✓ Authorize Controlled Rebaseline
✓ Protect Key Performance Indicator (KPI)/Net Present Value (NPV) Timeline
CR-002 DOES NOT
✗ Add Scope
✗ Change Deliverables
✗ Modify Deliverables 1-7 (D1-D7) Structure

## Slide 6
Three Possible Outcomes — One Must Be Recorded Today
The Change Control Board (CCB) and Board of Governors (BOG) must record a formal decision on Change Request CR-002 (CR-002) today. Under Pole Trust Bank Change Policy (PTB-CHG-001), there are exactly three valid outcomes. There is no fourth option. Failure to decide is itself a decision and will be recorded as such.
Deferred
Postpone decision today
Rejected
Deny the change request
Approved
Accept Change Request CR-002 (CR-002) as-is
Start
Begin decision process
✓ APPROVED
Enters the baseline.
✗ REJECTED
Baseline stays unchanged.
⏸ DEFERRED
Postponed to a future review date.
Governance Imperative: Every outcome must be logged. Silence is not neutrality under Pole Trust Bank Change Policy (PTB-CHG-001).

## Slide 7
What Makes a Valid Change Control Baseline?
01
Written Change Form with Unique ID
COMPLETE ✓
02
Reason Stated Clearly
COMPLETE ✓
03
Impact Verified Across All 5 Dimensions
COMPLETE ✓
04
Justification Grounded in Data
COMPLETE ✓
05
Change Control Board (CCB) Decision Formally Recorded
PENDING ⏳
06
All Items Logged in the Change Log
IN PROGRESS ⏳