## Slide 1
PTB-STS-001 | MONTH 10 OF 24
Project Health & Status Report
Pole Trust Bank | AI Banking Transformation
Reporting Period
Month 10 of 24
Overall RAG Status
AMBER — LAGGING
Reported To
Project Sponsor & Executive Steering Committee

## Slide 2
EXECUTIVE DASHBOARD
At a Glance — Month 10 of 24
Four EVM indicators define the project's Month 10 health. Schedule and cost performance are in the red zone. Two amber signals require immediate Sponsor attention.
40%
Progress Earned
Planned: 50% | 10% gap on critical path
0.80
Schedule Index
SPI = 0.80 | SV = −10% | 10% behind critical path
0.89
Cost Index
CPI = 0.89 | CV = −12% | 12% over phase budget
$11.5M
CAPEX Budget
TCO: $27.5M | DEC-02 funding pending
The 10% Gap — Stated Plainly
Planned: 50%. Earned: 40%. The 10% shortfall is a schedule variance that compounds across the zero-slack critical path. Every week of delay flows one-for-one to the D7 completion date.
Bad news stated plainly. Sponsor decisions fund recovery.

## Slide 3
SCOPE & ROADMAP
Project Scope — 7 Deliverables, 48 Work Packages, 24 Months
Seven sequential deliverables (D1–D7) form a zero-slack critical path. D2 and D3 carry active delays — each week of slippage flows one-for-one to D7. No float exists on this chain.
Critical Path Warning
D1 to D7 = Zero-slack critical path. Every D2 slip flows one-for-one to D7.
D2 and D3 delays have already consumed the schedule float.
No recovery is possible without Sponsor-approved intervention.
Scope & Budget Reference
Scope Document: PTB-SCOPE-001
CAPEX Envelope: USD 11.5M
Total Cost of Ownership: USD 27.5M
Work Packages: 48 across 7 deliverables
Program Duration: 24 months

## Slide 4
MILESTONE TRACKER
Milestone Tracker — What's On Track, What's Not
Five gate milestones define the program's critical path. M0 and M1 are approved and closed. M2 and M3 are red — delayed by approximately 2 to 3 months. M4 is amber and at risk of slipping if D2/D3 recovery does not accelerate immediately.
1
M0 — Schedule Baseline Approved
Baseline formally approved. Schedule governance active.
2
M1 — Charter & Funding Gate (End M02)
Charter signed. Funding gate cleared. Program authorized.
3
M2 — Foundation Accepted / D2 (End M04)
Data & vendor gaps not resolved in time. Foundation acceptance delayed.
4
M3 — Copilot Pilot Live / D3 (End M07)
D2 delay cascaded to D3. Copilot pilot launch pushed back.
5
M4 — Customer Assistant Pilot / D4 (End M11)
Contingent on D2/D3 recovery. Slippage risk is active.
Root Cause
Late D2 start — data gaps and vendor onboarding not resolved in time. D3 is single-threaded with no parallel path. Slip flows 1-for-1 on the zero-slack critical path.
Recovery Action
Crash D2/D3 schedules. Parallelize activities. Enforce COTS-First sourcing. Accelerate specialist staffing. Rebaseline via CR-002 with Sponsor approval.

## Slide 5
COST & EVM PERFORMANCE
Budget Performance — Earned Value Management Deep Dive
Month 10 EVM data confirms cost pressure. CPI at 0.89 means the project receives 89 cents of earned value per dollar spent. CV at −12% confirms a USD 1.38M cost overrun against phase budget. Contingency is being consumed faster than planned.
Cost Variance (CV)
−12% | EV minus AC is negative | Over budget by phase
Cost Performance Index
CPI = 0.89 | Getting 89 cents per dollar spent
Contingency Status
Early-burn flag active | Consumed faster than planned
Root Cause — Cost Pressure
Heavier D2/D3 specialist effort than planned. Extended vendor procurement windows. Early contingency draw. All variances remain within the USD 11.5M CAPEX / USD 27.5M TCO envelope — but trajectory requires intervention.
Recovery Actions — Cost Control
DEC-02 funding release to unlock phase budget
CR-002 rebaseline to reset EVM baselines
COTS-First sourcing to reduce specialist dependency
Weekly CPI tracking with CFO, Sponsor, PM, Finance, PMO

## Slide 6
RISK REGISTER
Risks & Issues — What's Fired, What's Rising
Five active risks span the program. Two are red and require immediate action. Three are amber and under active monitoring. Every risk has an owner, an action, and a decision route to the Sponsor.
RED — Integration Failure (D2) — FIRED
API and data profiling gaps threaten D2 delivery. Front-load profiling activities. Decision deadline: DEC-10. Owner: Tech Lead | Action Owner: Data Architect
RED — Vendor / Platform Slip — RISING
Platform vendor delays compound D2 schedule risk. Early sourcing required. Sponsor decision needed: DEC-07. Owner: Procurement | Action Owner: Vendor Manager
AMBER — Staff / Capacity Gap — RISING
Specialist AI and data roles remain unfilled. Role appointments required by DEC-05 / DEC-06. Owner: HR Partner | Action Owner: Project Manager
AMBER — Hallucination / Model Risk — MONITORING
LLM output accuracy risk in Copilot and Customer Assistant. Retrieval controls and pilot gates active. Owner: AI Quality Lead | Action Owner: Model Governance Team
AMBER — Regulatory Concern — MONITORING
AI compliance evidence requirements evolving. Compliance evidence pack due: DEC-09. Owner: Compliance Officer | Action Owner: Legal & Compliance
Every risk has an owner, an action, and a decision route to the Sponsor.

## Slide 7
SPONSOR DECISIONS REQUIRED
Sponsor Decisions Required — Three Calls, One Board Meeting
Three Sponsor decisions are required to authorize recovery. Each has a defined decision reference, an owner, and a deadline. No scope is added — funding and rebaseline authority flow through CR-002.
1
DEC-01 — Record Effective Start Date
Formally record the program's effective start date. Baseline for all EVM calculations depends on this authorization.
2
DEC-02 — Release Phase Funding
Release phase funding to unlock D2/D3 recovery. Implemented via CR-002 / PTB-CHG-001. Contingency draw and specialist staffing depend on this release.
3
DEC-03 — Delegate PM Authority to Salman Zaman
Formally delegate Program Manager authority to Salman Zaman. Recovery execution requires clear, authorized leadership.
Funding & rebaseline authority flows through CR-002 — the CCB-approved change-control firewall. No scope is added. Funding + rebaseline only. Baseline moves only through an approved CR.